## Project_Work_Order6388059447436
Project Work Order
From 13 Mar 2018 To 19 Apr 2025
Page 1 of 1
Total Records: 78 Records 1 To 78
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Debit_Amt | Credit_Amt | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Building | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date | Completed_Per
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1201 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1250 | 22 | 27500 | 0 | 27500 | 5 | 1159.875 | 25517.25 | 0 | 0 | 0 | 25517.25 | 90.125 | 1982.75 | Typical flat ceiling punning work. |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | pur.nrpl2 | 10 Mar 2021 | 92.79
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1202 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1250 | 22 | 27500 | 0 | 27500 | 5 | 1250 | 27500 | 0 | 0 | 0 | 27500 | 0 | 0 | Typical flat ceiling punning work. |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | pur.nrpl2 | 10 Mar 2021 | 100
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1301 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1250 | 22 | 27500 | 0 | 27500 | 5 | 1071.5 | 23573 | 0 | 0 | 0 | 23573 | 178.5 | 3927 | Typical flat ceiling punning work. |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | pur.nrpl2 | 10 Mar 2021 | 85.72
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1302 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1250 | 22 | 27500 | 0 | 27500 | 5 | 1148 | 25256 | 0 | 0 | 0 | 25256 | 102 | 2244 | Typical flat ceiling punning work. |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | pur.nrpl2 | 10 Mar 2021 | 91.84
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1401 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1250 | 22 | 27500 | 0 | 27500 | 5 | 1068 | 23496 | 0 | 0 | 0 | 23496 | 182 | 4004 | Typical flat ceiling punning work. |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | pur.nrpl2 | 10 Mar 2021 | 85.44
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1402 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1250 | 22 | 27500 | 0 | 27500 | 5 | 995 | 21890 | 0 | 0 | 0 | 21890 | 255 | 5610 | Typical flat ceiling punning work. |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | pur.nrpl2 | 10 Mar 2021 | 79.6
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1501 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1250 | 22 | 27500 | 0 | 27500 | 5 | 1134 | 24948 | 0 | 0 | 0 | 24948 | 116 | 2552 | Typical flat ceiling punning work. |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | pur.nrpl2 | 10 Mar 2021 | 90.72
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1502 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1250 | 22 | 27500 | 0 | 27500 | 5 | 1250 | 27500 | 0 | 0 | 0 | 27500 | 0 | 0 | Typical flat ceiling punning work. |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | pur.nrpl2 | 10 Mar 2021 | 100
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1601 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1250 | 22 | 27500 | 0 | 27500 | 5 | 1250 | 27500 | 0 | 0 | 0 | 27500 | 0 | 0 | Typical flat ceiling punning work. |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | pur.nrpl2 | 10 Mar 2021 | 100
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1602 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1250 | 22 | 27500 | 0 | 27500 | 5 | 1250 | 27500 | 0 | 0 | 0 | 27500 | 0 | 0 | Typical flat ceiling punning work. |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | pur.nrpl2 | 10 Mar 2021 | 100
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1701 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1250 | 22 | 27500 | 0 | 27500 | 5 | 1238 | 27236 | 0 | 0 | 0 | 27236 | 12 | 264 | Typical flat ceiling punning work. |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | pur.nrpl2 | 10 Mar 2021 | 99.04
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1702 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1250 | 22 | 27500 | 0 | 27500 | 5 | 1250 | 27500 | 0 | 0 | 0 | 27500 | 0 | 0 | Typical flat ceiling punning work. |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | pur.nrpl2 | 10 Mar 2021 | 100
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 801 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1250 | 22 | 27500 | 0 | 27500 | 5 | 1221.5 | 26873 | 0 | 0 | 0 | 26873 | 28.5 | 627 | Typical flat ceiling punning work. |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | pur.nrpl2 | 10 Mar 2021 | 97.72
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 802 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1250 | 22 | 27500 | 0 | 27500 | 5 | 1221.5 | 26873 | 0 | 0 | 0 | 26873 | 28.5 | 627 | Typical flat ceiling punning work. |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | pur.nrpl2 | 10 Mar 2021 | 97.72
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 901 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1250 | 22 | 27500 | 0 | 27500 | 5 | 1250 | 27500 | 0 | 0 | 0 | 27500 | 0 | 0 | Typical flat ceiling punning work. |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | pur.nrpl2 | 10 Mar 2021 | 100
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 902 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1250 | 22 | 27500 | 0 | 27500 | 5 | 1054.5 | 23199 | 0 | 0 | 0 | 23199 | 195.5 | 4301 | Typical flat ceiling punning work. |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | pur.nrpl2 | 10 Mar 2021 | 84.36
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1001 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1250 | 22 | 27500 | 0 | 27500 | 5 | 1198 | 26356 | 0 | 0 | 0 | 26356 | 52 | 1144 | Typical flat ceiling punning work. |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | pur.nrpl2 | 10 Mar 2021 | 95.84
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1002 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1250 | 22 | 27500 | 0 | 27500 | 5 | 1198 | 26356 | 0 | 0 | 0 | 26356 | 52 | 1144 | Typical flat ceiling punning work. |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | pur.nrpl2 | 10 Mar 2021 | 95.84
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1101 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1250 | 22 | 27500 | 0 | 27500 | 5 | 1237.5 | 27225 | 0 | 0 | 0 | 27225 | 12.5 | 275 | Typical flat ceiling punning work. |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | pur.nrpl2 | 10 Mar 2021 | 99
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1102 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1250 | 22 | 27500 | 0 | 27500 | 5 | 1205.83 | 26528.26 | 0 | 0 | 0 | 26528.26 | 44.17 | 971.74 | Typical flat ceiling punning work. |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | pur.nrpl2 | 10 Mar 2021 | 96.4664
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1902 COLOUR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1500 | 22 | 33000 | 0 | 33000 | 5 | 1500 | 33000 | 0 | 0 | 0 | 33000 | 0 | 0 | LABOR FOR CEILING PUNNING WORK Tower & Floor : TOWER B : 101-102, 201-202, 301-302, 401-402, 501-502, 601-602, 701-702, 801-802, 901-902, 1001-1002, 1101-1102, 1201-1202, 1301-1302, 1401-1402, 1501-1502, 1601-1602, 1701-1702, 1801-1802, 1901-1902 TOWER C : 101-102, 201-202, 301-302, 401-402, 501-502, 601-602, 701-702, 801-802, 901-902, 1001-1002, 1101-1102, 1201-1202, 1301-1302, 1401-1402, 1501-1502, 1601-1602, 1701-1702, 1801-1802, 1901-1902 Qty : TOWER B : 101-102, 201-202, 301-302, 401-402, 501-502, 601-602, 701-702, = 1500 Sq.Ft. (In Each & Every Unit) 801-802, 901-902, 1001-1002, 1101-1102, 1201-1202, 1301-1302, 1401-1402, 1501-1502, 1601-1602, 1701-1702, = 250 SqFt.(In Each & Every Unit) 1801-1802, 1901-1902 = 1500 Sq.Ft.(In Each & Every Unit) |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1901 COLOUR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1500 | 22 | 33000 | 0 | 33000 | 5 | 1500 | 33000 | 0 | 0 | 0 | 33000 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1802 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1500 | 22 | 33000 | 0 | 33000 | 5 | 1500 | 33000 | 0 | 0 | 0 | 33000 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1801 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1500 | 22 | 33000 | 0 | 33000 | 5 | 1500 | 33000 | 0 | 0 | 0 | 33000 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1702 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 250 | 22 | 5500 | 0 | 5500 | 5 | 250 | 5500 | 0 | 0 | 0 | 5500 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1701 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 250 | 22 | 5500 | 0 | 5500 | 5 | 250 | 5500 | 0 | 0 | 0 | 5500 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1602 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 250 | 22 | 5500 | 0 | 5500 | 5 | 250 | 5500 | 0 | 0 | 0 | 5500 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1601 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 250 | 22 | 5500 | 0 | 5500 | 5 | 250 | 5500 | 0 | 0 | 0 | 5500 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1502 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 250 | 22 | 5500 | 0 | 5500 | 5 | 250 | 5500 | 0 | 0 | 0 | 5500 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1501 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 250 | 22 | 5500 | 0 | 5500 | 5 | 250 | 5500 | 0 | 0 | 0 | 5500 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1402 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 250 | 22 | 5500 | 0 | 5500 | 5 | 250 | 5500 | 0 | 0 | 0 | 5500 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1401 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 250 | 22 | 5500 | 0 | 5500 | 5 | 250 | 5500 | 0 | 0 | 0 | 5500 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1302 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 250 | 22 | 5500 | 0 | 5500 | 5 | 250 | 5500 | 0 | 0 | 0 | 5500 | 0 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1301 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 250 | 22 | 5500 | 0 | 5500 | 5 | 78 | 1716 | 0 | 0 | 0 | 1716 | 172 | 3784 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 31.2
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1202 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 250 | 22 | 5500 | 0 | 5500 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1201 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 250 | 22 | 5500 | 0 | 5500 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1102 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 250 | 22 | 5500 | 0 | 5500 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1101 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 250 | 22 | 5500 | 0 | 5500 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1002 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 250 | 22 | 5500 | 0 | 5500 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 1001 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 250 | 22 | 5500 | 0 | 5500 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 902 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 250 | 22 | 5500 | 0 | 5500 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 901 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 250 | 22 | 5500 | 0 | 5500 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 802 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 250 | 22 | 5500 | 0 | 5500 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 801 COLOUR WORK PUNNING WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 250 | 22 | 5500 | 0 | 5500 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 702 COLOUR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1500 | 22 | 33000 | 0 | 33000 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 701 COLOUR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1500 | 22 | 33000 | 0 | 33000 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 602 COLOUR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1500 | 22 | 33000 | 0 | 33000 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 601 COLOUR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1500 | 22 | 33000 | 0 | 33000 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 502 COLOUR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1500 | 22 | 33000 | 0 | 33000 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 501 COLOUR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1500 | 22 | 33000 | 0 | 33000 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 402 COLOUR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1500 | 22 | 33000 | 0 | 33000 | 5 | 471 | 10362 | 0 | 0 | 0 | 10362 | 1029 | 22638 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 31.4
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 401 COLOUR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1500 | 22 | 33000 | 0 | 33000 | 5 | 484 | 10648 | 0 | 0 | 0 | 10648 | 1016 | 22352 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 32.2667
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 302 COLOUR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1500 | 22 | 33000 | 0 | 33000 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 301 COLOUR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1500 | 22 | 33000 | 0 | 33000 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 0
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 202 COLOUR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1500 | 22 | 33000 | 0 | 33000 | 5 | 431.225 | 9486.95 | 0 | 0 | 0 | 9486.95 | 1068.775 | 23513.05 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 28.7483
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 201 COLOUR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1500 | 22 | 33000 | 0 | 33000 | 5 | 426.175 | 9375.85 | 0 | 0 | 0 | 9375.85 | 1073.825 | 23624.15 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 28.4117
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 102 COLOUR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1500 | 22 | 33000 | 0 | 33000 | 5 | 437.5 | 9625 | 0 | 0 | 0 | 9625 | 1062.5 | 23375 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 29.1667
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | B 101 COLOUR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 1500 | 22 | 33000 | 0 | 33000 | 5 | 242.5 | 5335 | 0 | 0 | 0 | 5335 | 1257.5 | 27665 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 16.1667
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | TOWER B 1ST FLOOR COMMON PAINT & COLOR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 410 | 22 | 9020 | 0 | 9020 | 5 | 268 | 5896 | 0 | 0 | 0 | 5896 | 142 | 3124 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 65.3659
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | TOWER B TERRACE COMMON PAINT & COLOR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 410 | 22 | 9020 | 0 | 9020 | 5 | 338 | 7436 | 0 | 0 | 0 | 7436 | 72 | 1584 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 82.439
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | TOWER B 2ND FLOOR COMMON PAINT & COLOR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 410 | 22 | 9020 | 0 | 9020 | 5 | 268 | 5896 | 0 | 0 | 0 | 5896 | 142 | 3124 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 65.3659
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | TOWER B 4TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 410 | 22 | 9020 | 0 | 9020 | 5 | 268 | 5896 | 0 | 0 | 0 | 5896 | 142 | 3124 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 65.3659
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | TOWER B 7TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 410 | 22 | 9020 | 0 | 9020 | 5 | 268 | 5896 | 0 | 0 | 0 | 5896 | 142 | 3124 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 65.3659
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | TOWER B 3RD FLOOR COMMON PAINT & COLOR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 410 | 22 | 9020 | 0 | 9020 | 5 | 268 | 5896 | 0 | 0 | 0 | 5896 | 142 | 3124 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 65.3659
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | TOWER B 8TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 410 | 22 | 9020 | 0 | 9020 | 5 | 268 | 5896 | 0 | 0 | 0 | 5896 | 142 | 3124 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 65.3659
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | TOWER B 9TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 410 | 22 | 9020 | 0 | 9020 | 5 | 268 | 5896 | 0 | 0 | 0 | 5896 | 142 | 3124 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 65.3659
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | TOWER B 14TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 410 | 22 | 9020 | 0 | 9020 | 5 | 352.8 | 7761.6 | 0 | 0 | 0 | 7761.6 | 57.2 | 1258.4 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 86.0488
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | TOWER B 15TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 410 | 22 | 9020 | 0 | 9020 | 5 | 352.8 | 7761.6 | 0 | 0 | 0 | 7761.6 | 57.2 | 1258.4 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 86.0488
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | TOWER B 5TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 410 | 22 | 9020 | 0 | 9020 | 5 | 268 | 5896 | 0 | 0 | 0 | 5896 | 142 | 3124 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 65.3659
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | TOWER B 6TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 410 | 22 | 9020 | 0 | 9020 | 5 | 268 | 5896 | 0 | 0 | 0 | 5896 | 142 | 3124 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 65.3659
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | TOWER B 10TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 410 | 22 | 9020 | 0 | 9020 | 5 | 268 | 5896 | 0 | 0 | 0 | 5896 | 142 | 3124 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 65.3659
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | TOWER B 11TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 410 | 22 | 9020 | 0 | 9020 | 5 | 268 | 5896 | 0 | 0 | 0 | 5896 | 142 | 3124 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 65.3659
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | TOWER B 12TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 410 | 22 | 9020 | 0 | 9020 | 5 | 268 | 5896 | 0 | 0 | 0 | 5896 | 142 | 3124 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 65.3659
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | TOWER B 16TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 410 | 22 | 9020 | 0 | 9020 | 5 | 352.8 | 7761.6 | 0 | 0 | 0 | 7761.6 | 57.2 | 1258.4 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 86.0488
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | TOWER B 17TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 410 | 22 | 9020 | 0 | 9020 | 5 | 352.8 | 7761.6 | 0 | 0 | 0 | 7761.6 | 57.2 | 1258.4 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 86.0488
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | TOWER B 18TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 410 | 22 | 9020 | 0 | 9020 | 5 | 352.8 | 7761.6 | 0 | 0 | 0 | 7761.6 | 57.2 | 1258.4 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 86.0488
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | TOWER B 19TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 410 | 22 | 9020 | 0 | 9020 | 5 | 70 | 1540 | 0 | 0 | 0 | 1540 | 340 | 7480 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 100
GREENWOOD ASPIRE EXP | 69 | 0 | 11 Feb 2021 | Irfan Abdul | TOWER B 13TH FLOOR COMMON PAINT & COLOR WORK | LABOR FOR CEILING PUNNING WORK | SQFT | 410 | 22 | 9020 | 0 | 9020 | 5 | 268 | 5896 | 0 | 0 | 0 | 5896 | 142 | 3124 |  |  | T.Joshi | pur.nrpl2 | T.Joshi | Job Work |  |  |  | Approved | T.Joshi |  | 65.3659